## Feuil1
Tool 4.2: Template of a method for calculating the time commitment of staff and salary costs of a project
Think it Through Exercise for Project Inputs - How much time (in days) will each project activity need to be completed? Based on the separated Project Activities from Tool 4.1 (Table 3), estimating who is doing what and how much time it will take them?
Step 1: Building on the information developed in 4.1 (Table 3), estimate here in Table 8 how long it will take each person to do their tasks/sub-tasks in days.
Step 2: Specify when the activity will start and finish (you don't need to use specific dates, just project months (i.e. Month 2 to Month 4; etc.)
Fields with pre-designed calculations |  | Total of Partner | Overall Project Total
Table 8: Estimating the Timeframe of each Project Activity
Project Activity | What needs to be done? |  | Who is involved and for what role? (Lead Partner, Project Partner, External Service Provider) |  |  |  | How long will it take? | When will the activity be in operation?
| Task | Sub-Task | Person (if known) | Organisation | Position | Role in this Task/Sub-task | Estimated Number of Days | Start date | End date
use Tool 4.1 | use Tool 4.1 | use Tool 4.1 | use Tool 4.1 | use Tool 4.1 | use Tool 4.1 | use Tool 4.1
Staff time needed for Activity 1 | [6 empty] | 0
Staff time needed for Activity 2 | [6 empty] | 0
Staff time needed for Activity 3 | [6 empty] | 0
Staff time needed for Activity 4 | [6 empty] | 0
Total staff time needed for Project | [6 empty] | 0
Think Through Exercise: Project Inputs - By Partner and Years (in days)
Step 3: Using the information of Table 8, identify the involvement for each person/position per partner organisation and their staff, sum up their days for each project activity and write the days into Table 9.
Step 4: If your project is longer than one year, it is useful to do this exercise for each year and then a total table (summing up all years). You can use the Multi Cause and Timing Diagram Tool in Stop 2.2 to help this task.
Table 9: Project Inputs By Partner Organisation and Years (in days)
Year 1 | Lead Partner |  |  |  |  | Project Partner A | [5 empty] | Project Partner B | [5 empty] | All Project Organisations
| Staff A | Staff B | Staff C | Staff D | Total | Staff A | Staff B | Staff C | Staff D | Staff E | Total | Staff A | Staff B | Staff C | Staff D | Staff E | Total |  | 0
Project Activity 1 | [5 empty] | 0 | [11 empty] | 0 | 0
Project Activity 2 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0
Project Activity 3 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0
Project Activity 4 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0
Year 1 involvement in Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Year 2 | Lead Partner |  |  |  |  | Project Partner A | [5 empty] | Project Partner B
| Staff A | Staff B | Staff C | Staff D | Total | Staff A | Staff B | Staff C | Staff D | Staff E | Total | Staff A | Staff B | Staff C | Staff D | Staff E | Total
Project Activity 1 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0
Project Activity 2 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0
Project Activity 3 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0
Project Activity 4 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0
Year 2 Involvement in Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
All years | Lead Partner |  |  |  |  | Project Partner A | [5 empty] | Project Partner B
| Staff A | Staff B | Staff C | Staff D | Total | Staff A | Staff B | Staff C | Staff D | Staff E | Total | Staff A | Staff B | Staff C | Staff D | Staff E | Total
Project Activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Activity 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Involvement in Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Think Through Exercise: Converting the Estimated Project Days into Salary Costs
(at the moment this is an example of a filled in salary costing sheet for a partnership of four organisations) Please find an empty template below
Step 5: Utilise the information from Table 8 and populate Table 10 with the staff positions for each organisation (LP and PPs) who are involved in the project. Obtain their employment details (i.e. annual salary, contracted days per week).
Step 6: Utilise the information from Table 9 and populate Table 10 with the number of days input for each person/position involved in the project per year.
Step 7: Review the table inputs and results and check if a staff/position has been allocated too many days, and if their time allocation is in line with their role.
Note: Table 10 is based on the specified number of days on the project for each project team member.
Colour Code:
Fields for you to put in the relevant information and data
Fields with pre-designed calculations |  | Total for each Partner | Overall Project Total
Table 10: Calculating the Project Salary Costs (EXAMPLE)
Lead Partner | Employment Details | Project Input and Salary Costs per Year | Total Costs
Project Team Member | Position | Annual gross salary (as stated on the payslip) | Contracted days per week | Contracted days per month | Contracted days per year | Project Days Allocated in Year 1 | Percentage of his/her time spent on project in Year 1 | Project Salary Costs in Year 1 | Project Days Allocated in Year 2 | Percentage of his/her time spent on project in Year 2 | Project Salary Costs in Year 2 | Total Salary Costs for Project (Year 1+2)
A | Project Manager | 65000 | 5 | 21.79 | 261.48 | 125 | 47.8% | 31073.1222 | 0 |  |  | 31073.1222
B | Senior Project Officer | 38000 | 5 | 21.79 | 261.48 | 200 | 76.49% | 29065.3205 | 0 |  |  | 29065.3205
C | Project Officer | 32750 | 5 | 21.79 | 261.48 | 200 | 76.49% | 25049.717 | 0 |  |  | 25049.717
D | Finance Officer | 23000 | 5 | 21.79 | 261.48 | 30 | 11.47% | 2638.8251 | 0 |  |  | 2638.8251
|  |  |  | 21.79 | 261
Total Project Salary Costs for Lead Partner | [5 empty] | 555 |  | 87826.9849 | 0 |  |  | 87826.9849
Partner 1 | Employment Details | Project Input and Salary Costs per Year | Total Costs
Project Team Member | Position | Annual gross salary (as stated on the payslip) | Contracted days per week | Contracted days per month | Contracted days per year | Project Days Allocated in Year 1 | Percentage of his/her time spent on project in Year 1 | Project Salary Costs in Year 1 | Project Days Allocated in Year 2 | Percentage of his/her time spent on project in Year 2 | Project Salary Costs in Year 2 | Total Salary Costs for Project (Year 1+2)
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! |  |  |  | #DIV/0!
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! |  |  |  | #DIV/0!
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! |  |  |  | #DIV/0!
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! |  |  |  | #DIV/0!
|  |  |  | 21.79 | 261
Total Project Salary Costs for Partner 1 | [5 empty] | 0 |  |  | 0
Partner 2 | Employment Details | Project Input and Salary Costs per Year | Total Costs
Project Team Member | Position | Annual gross salary (as stated on the payslip) | Contracted days per week | Contracted days per month | Contracted days per year | Project Days Allocated in Year 1 | Percentage of his/her time spent on project in Year 1 | Project Salary Costs in Year 1 | Project Days Allocated in Year 2 | Percentage of his/her time spent on project in Year 2 | Project Salary Costs in Year 2 | Total Salary Costs for Project (Year 1+2)
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! |  |  |  | #DIV/0!
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! |  |  |  | #DIV/0!
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! |  |  |  | #DIV/0!
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! |  |  |  | #DIV/0!
|  |  |  | 21.79 | 261
Total Project Salary Costs for Partner 2 | [5 empty] | 0 |  |  | 0
Total Project Days and Salary Costs across all Partner Organisations | [5 empty] | 555 |  | 87826.9849 | 0 |  |  | 87826.9849
Total Project Days and Salary Costs | [5 empty] | 965 |  | € 122,038.01 | 645 |  | € 77,070.90 | € 199,108.92